## Test Plan
Sheet 1: Test Plan
Test Plan ID | TP1
Test Plan Name | MinIO File Compression and Email
Description | Test the Airflow DAG that compresses files uploaded to MinIO and sends email
Scope | Verify file compression and email
Test Objectives | 1. Validate DAG triggers on file upload
2. Ensure file is compressed correctly
3. Confirm email contains correct file specifications
Test Environment | Airflow 3.0
MinIO
SMTP server (Gmail)
Python 3.12
Test Strategy | 1. Functional Testing
2. Integration Testing
3. Negative Testing
Entry Criteria | 1. Airflow and MinIO are set up
2. Test files are ready
3. SMTP server is configured
Exit Criteria | 1. All test cases pass
2. No defects remain
Schedule | Start: 2025-04-23
End: 2025-04-23
Risks | 1. MinIO connectivity issues
2. Email server downtime

## Test Cases
Sheet 2: Test Cases
ID | Module | Sub-module | Items | Steps | Expected Outcome | Actual Outcome | Remarks
TC001 | File Upload | MinIO Integration | File Detection | 1. Upload a text file of about 1MB to MinIO shared folder | Airflow DAG is triggered upon file upload | The task 'wait_for_file' recognizes the file and moves to the next task. | Test with different file sizes
TC002 | File Upload | MinIO Integration | Invalid File Type | 1. Upload a non-supported file type (.exe) | DAG does not trigger, no compression occurs | The executable file also uploads and compresses, which can be seen as a security vulnerability. | Verify error handling
TC003 | File Compression | Compression Logic | File Compression | 1. Upload a text file to MinIO shared folder | Compressed zip file is created in MinIO with reduced size | Original File: Programs.docx, Size: 26007 bytes Compressed File: Programs.docx.zip, Size: 22351 bytes | Check compression ratio
2. DAG triggers and compresses file to .zip format
TC004 | File Compression | Compression Logic | Large File | 1. Upload a large file | Compressed file is created without errors; size is reduced | Original File: Electron arrangement in an atom_2.mp4, Size: 213233428 bytes Compressed File: Electron arrangement in an atom_2.mp4.zip, Size: 212988754 bytes | Test system stability
TC005 | Email Notification | SMTP Integration | Email Content | 1. Upload a text file | Email contains specifications: original file name and size, compressed file name and size | Email Subject: File Compression Report | Verify email format
|  |  |  | 2. DAG compresses file |  | Contents: Original File: Electron arrangement in an atom_2.mp4, Size: 213233428 bytes Compressed File: Electron arrangement in an atom_2.mp4.zip, Size: 212988754 bytes
3. Email is sent
TC006 | Email Notification | SMTP Integration | Invalid Email Config | 1. Configure invalid SMTP server | Email is not sent, error is logged in Airflow | [2025-04-23, 10:57:06 UTC] {logging_mixin.py:190} INFO - Task:<Task(EmailOperator): send_email> dag:<DAG: compress_file_on_upload> [2025-04-23, 10:57:06 UTC] {logging_mixin.py:190} INFO - Failure caused by (530, b'5.7.0 Authentication Required. | Test error handling
2. Upload a file
TC007 | End-to-End | Full Workflow | Complete Process | 1. Upload a text file | File is compressed and stored in MinIO, email with correct specs is received | File is uploaded to uploads folder, moves to processed folder and compressed file is correctly stored in compressed folder of MinIO | Validate entire workflow
2. DAG compresses file
3. Email is sent
TC008 | End-to-End | Full Workflow | No File Uploaded | 1. Monitor MinIO folder with no file upload | DAG does not trigger | DAG triggers every one minute and waits for file. The wait is rescheduled to wait again after every 5 minutes. As DAG triggers and waits every 1 minute. Multiple DAGs are created with no file input. | Test idle state